## Requirements
id	Requirement Description	work / required / (Units)	work / done / (Units)	task / completed / (%)
1	user can create albums and upload images	100.00	66.67	66.67%
2	Albums or images can be deleted or renamed	100.00	0.00	0.00%
3	albums can be downloaded as zip file	100.00	0.00	0.00%
4	Has Admin and User roles where:	100.00	100.00	100.00%
5	Admin can create/delete/reset users or admins	100.00	0.00	0.00%
6	Admin can view albums of all users	100.00	0.00	0.00%
7	Users can only view their own albums	100.00	0.00	0.00%
Total		700.00	166.67	23.81%

## Tasks
id	main task description	sub task description	work / required / (Units)	Work / done / (Units)	task / completed / (%)
1.1	user can create albums and upload images	Backend - database structure	16.67	16.67	100.00%
1.2		Frontend - UI – page 1 – login	16.67	16.67	100.00%
1.3		Frontend - UI – page 2 – home admin	16.67	16.67	100.00%
1.4		Frontend - UI – page 3 – home user	16.67	16.67	100.00%
1.5		Frontend - UI – page 4 – home user create albums	16.67	0.00	0.00%
1.6		Frontend - UI – page 5 – home user upload images	16.67	0.00	0.00%
2	Albums or images can be deleted or renamed		100.00	0.00	0.00%
3	albums can be downloaded as zip file		100.00	0.00	0.00%
4	Has Admin and User roles where:		100.00	100.00	100.00%
5	Admin can create/delete/reset users or admins		100.00	0.00	0.00%
6	Admin can view albums of all users		100.00	0.00	0.00%
7	Users can only view their own albums		100.00	0.00	0.00%
Total :			700.00	166.67	23.81%